## Agile Backlog 1
Iteration 1 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 101. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority (light green)
Iteration 1
101 | Develop User model | 2 | ZP
102 | Develop Child model | 2 | ZP
103 | Design database schema | 3 | SV
104 | Create frontend points page | 4 | ZZ
105 | Develop Feedback model | 2 | ZP
106 | Design feedback page layout | 3 | SV
107 | Implement basic CRUD operations | 4 | ZZ
…
Iteration 2
201 | Integrate Points model | 3 | ZP
202 | Add points redemption feature | 4 | SV
203 | Optimize leaderboard display | 3 | ZZ
204 | Integrate Activity model | 3 | ZP
205 | Add filtering and export features | 4 | SV
206 | Improve UI responsiveness | 3 | ZZ
Iteration 3
301 | Integrate Volunteer model | 3 | ZP
302 | Add volunteer reporting feature | 4 | SV
303 | Optimize performance and security | 4 | ZZ
304 | Develop activity report submission | 3 | ZP
305 | Implement user notification feature | 4 | SV
306 | Prepare for production deployment | 3 | ZZ
| Medium Priority (light blue) |  |  | Note: assigned medium and low tasks are prioritized but not yet assigned to iteration, nor estimated.
Low Priority (pink)

## Iteration 1 Plan
Iteration Plan 1
Project | AfterSchool Ally
Team Names: | Zishang Peng, Shubham Verma, Zhuoran Zhang
Team Number: | 4
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
101 | Develop User model | ZP | Yes
102 | Develop Child model | ZP | Yes
103 | Design database schema | SV | Yes
104 | Create frontend points page | ZZ | Yes
105 | Develop Feedback model | ZP | Yes
106 | Design feedback page layout | SV | Yes
107 | Implement basic CRUD operations | ZZ | Yes
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
React&ReactNative | React for Web dev while ReactNative for mobile, may lead to inconsistent UI representation | ZP
Node.js | Server load may increase, requiring performance monitoring | ZP
MySQL | Data scale growth may impact query efficiency | ZP
3. Did your team visually track your progress by using tools such as Microsoft Project, SharePoint, Trello, etc.? Explain why you choose this tool.
Tracking Software Used | Why?
ClickUP | Automate, prioritize, and keep work moving—all while staying connected to Docs, Whiteboards, Chat, and more.
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Release Summary 1
Iteration 1: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception PD | Iteration #1 PD | Iteration #2 PD | Iteration #3 PD | Transition PD
|  | Due: | Due: | Due: | Due: | Due:
101 | Develop User model |  | 8
102 | Develop Child model |  | 8
103 | Design database schema |  | 12
104 | Create frontend points page |  | 16
105 | Develop Feedback model |  | 8
106 | Design feedback page layout |  | 12
107 | Implement basic CRUD operations |  | 16
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 320 | 0 | 0 | 0
Total Project Hours |  | 320

## Agile Backlog 2
Iteration 2 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority
Iteration 1
Iteration 2
201 | Integrate Points model | 3 | ZP
202 | Add points redemption feature | 4 | SV
203 | Optimize leaderboard display | 3 | ZZ
204 | Integrate Activity model | 3 | ZP
205 | Add filtering and export features | 4 | SV
206 | Improve UI responsiveness | 3 | ZZ
Iteration 3
301 | Integrate Volunteer model | 3 | ZP
302 | Add volunteer reporting feature | 4 | SV
303 | Optimize performance and security | 4 | ZZ
304 | Develop activity report submission | 3 | ZP
305 | Implement user notification feature | 4 | SV
306 | Prepare for production deployment | 3 | ZZ
Medium Priority
Low Priority

## Iteration 2 Plan
Iteration Plan 2
Project | AfterSchool Ally
Team Names: | Zishang Peng, Shubham Verma, Zhuoran Zhang
Team Number: | 4
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
201 | Integrate Points model | ZP | Yes
202 | Add points redemption feature | SV | Yes
203 | Optimize leaderboard display | ZZ | Yes
204 | Integrate Activity model | ZP | Yes
205 | Add filtering and export features | SV | Yes
206 | Improve UI responsiveness | ZZ | Yes
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
React&ReactNative | Code may need to refactory to adapt additional code | ZP
Node.js | Focus on async test | ZP
MySQL | Index may needed | ZP
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
ClickUP | no need to change, may need to pay for the increase of tracking task
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Release Summary 2
Iteration 2: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and tasks must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
201 | Integrate Points model |  |  | 12
202 | Add points redemption feature |  |  | 16
203 | Optimize leaderboard display |  |  | 12
204 | Integrate Activity model |  |  | 12
205 | Add filtering and export features |  |  | 16
206 | Improve UI responsiveness |  |  | 12
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 0 | 320 | 0 | 0
Total Project Hours |  | 320

## Agile Backlog 3
Iteration 3 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority
Iteration 1
Iteration 2
Iteration 3
301 | Integrate Volunteer model | 3 | ZP
302 | Add volunteer reporting feature | 4 | SV
303 | Optimize performance and security | 4 | ZZ
304 | Develop activity report submission | 3 | ZP
305 | Implement user notification feature | 4 | SV
306 | Prepare for production deployment | 3 | ZZ
Medium Priority
Low Priority

## Iteration 3 Plan
Iteration Plan 3
Project | AfterSchool Ally
Team Names: | Zishang Peng, Shubham Verma, Zhuoran Zhang
Team Number: | 4
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
301 | Integrate Volunteer model | ZP | YES
302 | Add volunteer reporting feature | SV | YES
303 | Optimize performance and security | ZZ | YES
304 | Develop activity report submission | ZP | YES
305 | Implement user notification feature | SV | YES
306 | Prepare for production deployment | ZZ | YES
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
React&ReactNative | Pre-production deploy may expose ui issues | ZP
Node.js | May stability matter | ZP
MySQL | Post-deployment may bring migration risk | ZP
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
ClickUP | Continues in use, may need to pay for the increase of tracking task
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Release Summary 3
Iteration 3: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
301 | Integrate Volunteer model |  |  |  | 12
302 | Add volunteer reporting feature |  |  |  | 16
303 | Optimize performance and security |  |  |  | 16
304 | Develop activity report submission |  |  |  | 12
305 | Implement user notification feature |  |  |  | 16
306 | Prepare for production deployment |  |  |  | 12
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 0 | 0 | 336 | 0
Total Project Hours |  | 336